## RACI Chart
The RACI Chart Template
Legend: | Yellow = input to edit Blue text = example, replace with your own
R = Responsible (does the work) A = Accountable (owns the outcome, signs off) C = Consulted (two-way input before the decision) I = Informed (one-way update after the decision)
Task / Decision | Exec. Sponsor | Impl. Manager | Engineering Lead | Customer Success | Client Admin
Define project scope & success criteria | A | R | C | C | C
Configure system & integrations | I | A | R | I | C
Data migration & validation | I | A | R | C | R
User acceptance testing | I | C | C | A | R
Client training | I | I | I | A | R
Go live | A | R | R | C | I
30 day post launch review | I | A | I | R | C

## Why & How to Use
Why & How to Use This Template
RACI stands for Responsible, Accountable, Consulted, and Informed. It assigns exactly one of those four roles to every person, for every task, on a project. The point isn't the chart itself, it's the conversation that happens while you build it. Most team friction doesn't come from bad people or bad plans, it comes from two people who both think they own a decision, or a task everyone assumed someone else was covering. RACI forces that ambiguity into the open before it costs you a missed deadline or an unhappy client.
Use case | Why this template helps
Cross functional projects | Anything that touches more than one team, like a client implementation that spans engineering, customer success, and sales, benefits from one shared map of ownership.
Recurring handoffs | Processes that repeat but keep breaking at the same seam, like a support ticket that bounces between teams, usually have an ownership gap a RACI chart will expose.
Onboarding new hires | Handing a new team member the chart teaches them the org's real decision map faster than any amount of explaining ever will.
Steering and exec reviews | When leadership needs a status update, the chart tells them exactly who to ask instead of routing every question through you.
How to fill it in
1. List the tasks first, not the people. Write down every meaningful task or decision the project requires down the left column, before you think about who's involved.
2. List every role that touches the work across the top. Use roles or titles rather than individual names so the chart still holds when someone changes seats.
3. Assign exactly one Accountable per row. If two people are Accountable for the same task, in practice nobody is.
4. Fill in Responsible, Consulted, and Informed. A task can have several Responsible parties, but keep Consulted and Informed lean, both slow a task down every time you add a name.
5. Review it with the group before you rely on it. Disagreements should surface here, in a meeting, instead of later, in a missed handoff.
Do
• Keep the chart to one page. If it needs a second tab, the project needs to be broken up.
• Revisit it at project milestones, ownership shifts as a project moves through phases.
• Use it in kickoff meetings so new stakeholders see the map on day one.
Don't
• Don't assign Accountable to a group or a title with three people in it, name the person.
• Don't confuse Consulted with Informed, one is a conversation, the other is a notice.
• Don't build it alone and hand it down, the buy-in happens in the building.