## Time Allocation
Time Allocation Template — Customer Onboarding
Legend: | Yellow = input to edit Blue text = editable assumption Grey row = phase subtotal See "Why & How to Use" tab for guidance
Assumptions
Hourly Rate ($) | 50
Onboarding Duration (weeks) | 14
Customers Onboarded / Month | 4
Phase | Step / Task | Owner / Role | Frequency | Hrs per Occurrence | # of Occurrences | Total Hours per Customer | % of Total Time | Tool / System | Automation Potential | Dependency (needs to happen first) | Cost per Customer | Notes
Pre-boarding Setup | Create internal items (Slack channel, Google Drive folder) | CS Ops | One-time | 0.1 | 1 | 0.1 | 0.0956% | Slack, Google Drive | High | Signed contract received | 5
Pre-boarding Setup | Sales to CS handoff meeting (set up by sales) | CSM | One-time | 1.5 | 1 | 1.5 | 1.434% | Zoom, CRM | Low | Deal closed in CRM | 75 | Sales schedules; CS attends
Pre-boarding Setup | Phase Subtotal |  |  |  |  | 1.6 |  |  |  |  | 80
Kickoff | Create kickoff deck and distribute for team updates (send to brokers for approval) | CSM | One-time | 4 | 1 | 4 | 3.824% | Slides/Deck tool | Medium | Handoff meeting complete | 200 | Loop in brokers for sign-off
Kickoff | Create ongoing notes doc | CSM | One-time | 0.5 | 1 | 0.5 | 0.478% | Google Docs | High | Kickoff deck created | 25
Kickoff | Conduct kickoff meeting | CSM | One-time | 2 | 1 | 2 | 1.912% | Zoom | Low | Deck approved | 100
Kickoff | Send kickoff meeting follow up notes | CSM | One-time | 1 | 1 | 1 | 0.956% | Email, Google Docs | Medium | Kickoff meeting held | 50
Kickoff | Phase Subtotal |  |  |  |  | 7.5 |  |  |  |  | 375
Implementation | Conduct weekly client meetings (agenda, notes, follow ups) | CSM | Weekly | 1 | 14 | 14 | 13.38% | Zoom, CRM | Low | Kickoff complete | 700 | 1 hr/week across onboarding duration
Implementation | Create and update project plan | CSM | Weekly | 1 | 10 | 10 | 9.56% | Project mgmt tool | Medium | Kickoff complete | 500 | Updated most weeks, not every week
Implementation | Data file in house (spec calls, follow ups, Q&A) | Implementation Eng | One-time | 12 | 1 | 12 | 11.47% | Internal data platform | Low | Customer data received | 600
Implementation | Internal ticket (create, track, follow up) | Implementation Eng | One-time | 5 | 1 | 5 | 4.78% | Jira/Ticketing | Medium | Data file started | 250
Implementation | Call with internal billing team | CSM | One-time | 3 | 1 | 3 | 2.868% | Zoom | Low | Contract terms confirmed | 150
Implementation | Create customer in system setup | Implementation Eng | One-time | 4 | 1 | 4 | 3.824% | Internal admin system | High | Ticket created | 200
Implementation | Ensure sFTP setup completion | Implementation Eng | One-time | 1.5 | 1 | 1.5 | 1.434% | sFTP | Medium | Customer created in system | 75
Implementation | Phase Subtotal |  |  |  |  | 49.5 |  |  |  |  | 2475
Training & Testing | Reporting call with customer | CSM | One-time | 5 | 1 | 5 | 4.78% | Zoom, Reporting tool | Low | sFTP setup complete | 250
Training & Testing | Test marketing/billing system | Implementation Eng | One-time | 10 | 1 | 10 | 9.56% | Billing platform | Medium | System setup complete | 500
Training & Testing | Customer system training | CSM | One-time | 3 | 1 | 3 | 2.868% | Zoom, LMS | Low | Testing complete | 150
Training & Testing | Member test | Implementation Eng | One-time | 5 | 1 | 5 | 4.78% | Internal test environment | Medium | Training scheduled | 250
Training & Testing | Phase Subtotal |  |  |  |  | 23 |  |  |  |  | 1150
Launch | Product team to review setup | Product | One-time | 1 | 1 | 1 | 0.956% | Internal admin system | Low | Member test passed | 50
Launch | Final launch readiness review | CSM | One-time | 4 | 1 | 4 | 3.824% | Checklist / Project mgmt tool | Medium | Product review passed | 200
Launch | Phase Subtotal |  |  |  |  | 5 |  |  |  |  | 250
Handoff | Onboarding to CSM handoff (notes, meetings) | CSM | One-time | 3 | 1 | 3 | 2.868% | Google Docs, Zoom | Medium | Launch complete | 150
Handoff | Phase Subtotal |  |  |  |  | 3 |  |  |  |  | 150
Ongoing / Other | Internal meetings/email/Slack to solve problems, develop solutions | CS Ops | Per Customer | 10 | 1 | 10 | 9.56% | Slack, Email | Low | N/A — spans whole project | 500
Ongoing / Other | External / other (one-off correspondence with clients, consultants, vendors) | CSM | Per Customer | 5 | 1 | 5 | 4.78% | Email | Low | N/A — spans whole project | 250
Ongoing / Other | Phase Subtotal |  |  |  |  | 15 |  |  |  |  | 750
GRAND TOTAL | Total time and cost per customer onboarded |  |  |  |  | 104.6 | 100% |  |  |  | 5230
Capacity Planning
Hours per Customer | 104.6
Monthly Hours Needed | 418.4
FTEs Needed (160 hrs/mo) | 2.615
Monthly Cost | 20920
How to use this template: update the yellow input cells with your own steps, owners, hours, and occurrences. Blue text marks assumptions to confirm (hourly rate, onboarding duration, customer volume). Automation Potential and Dependency columns help you spot where to invest in tooling and where handoffs create bottlenecks. Everything else recalculates automatically. See the "Why & How to Use" tab for the business cases this template supports.

## Why & How to Use
Why & How to Use This Template
A time allocation template breaks a repeatable process (like onboarding one customer) into every step, who owns it, how long it takes, and how often it happens. Once that's mapped, hours and cost per customer fall out as formulas instead of guesses.
Use case | Why this template helps
Pricing & quoting | Cost per customer (Total Hours × Hourly Rate) tells you the true delivery cost behind an onboarding fee, so you don't price below cost.
Headcount & capacity planning | Hours per customer × customers per month converts pipeline into FTEs needed, so you can hire ahead of a sales push instead of reacting to it.
Justifying a hire or a tool purchase to leadership | A phase level subtotal ($ and hours) turns "we're slammed" into a specific number leadership can act on.
Spotting automation opportunities | The Automation Potential column flags high-effort, low-complexity steps (data entry, notifications, ticket creation) that are good candidates to automate first.
Finding process bottlenecks | The Dependency column shows what has to finish before each step starts, surfacing handoffs that stall the whole timeline.
Comparing teams or segments | Duplicate the tab per team, segment, or customer tier (SMB vs Enterprise) to see where onboarding is heavier and why.
Benchmarking over time | Save a dated copy each quarter. A rising Hours per Customer number is an early signal that process, not headcount, needs attention.
Onboarding new CS/Implementation hires | The Step, Owner, and Tool columns double as a checklist and system list for someone new to the role.
How to fill it in
1. Set your Assumptions (hourly rate, onboarding duration, customers per month) at the top of the Time Allocation tab.
2. List every step in the process in the order it happens, grouped into phases.
3. Enter Hours per Occurrence and # of Occurrences for each step — most steps happen once; recurring ones (weekly meetings, updates) get real occurrence counts.
4. Tag Owner, Tool/System, Automation Potential, and Dependency for each step so the sheet doubles as a process map, not just a time log.
5. Check the Grand Total and Capacity Planning section — that's your real cost and staffing picture per customer.